Which journal to submit our paper to, and what to fix first

Group 7 · Vietnamese administrative-procedure assistant (System 3 + 4) · 18 October 2026 · journals only, no in-person presentation

Recommendation. Submit to a journal, not a conference: journals have no presentation and no travel, and the best options for us charge no fee. Finish the paper by mid-December 2026 and send it to the Vietnam Journal of Computer Science (VJCS): free, Scopus Q2, published by World Scientific, and its scope explicitly includes applications in administration. If our new human-labelled evaluation (section 5.3) comes out strong, try Artificial Intelligence and Law (Springer, free to publish) first; its editors decide quickly whether to send a paper to review, so a rejection costs us about a week. On AI use: every journal below allows AI assistance with disclosure, none allows an AI author, and all hold the human authors accountable for every claim and number.

# 1. Why a journal

Conferences require at least one author to register, travel and present (ICAIL 2027, for example, accepts remote presentation only “under exceptional circumstances”). Our team cannot present in person, so conferences are out. A journal works differently:

- We submit the manuscript online. There is no deadline.

- The editor checks fit and quality (days to a few weeks). Many papers are rejected here without review (“desk rejection”).

- Two or three anonymous reviewers read it (usually 1–4 months).

- We usually get “minor” or “major revision”: we fix the paper and write a point-by-point response letter. One or two rounds are normal.

- Accept or reject. Everything is in writing; nobody has to present or travel.

Two rules: we may send the paper to only one journal at a time, and a journal paper is longer and more complete than a conference paper (for example, up to about 7,000 words at JIT).

# 2. Journal options

Checked on 18 October 2026 from the journals’ own pages where possible. Items marked “check” come from secondary sources or conflict between sources.

| Journal | Publisher / indexing | Cost to us | Speed and selectivity | Fit and notes |
| --- | --- | --- | --- | --- |
| Vietnam Journal of Computer Science (VJCS) | World Scientific (Nguyen Tat Thanh University). Scopus CiteScore 3.0, Q2 (2024); JCR Q4, IF 0.8 | Free (sponsored by NTTU); open access | Review time not published (check). Historically about 1 in 6 papers accepted | Recommended. Broad CS with applications “in management, industry, engineering, administration and education”. Realistic for a student team. |
| Artificial Intelligence and Law | Springer. IF 3.1 (2024) | Free on the standard route; open access optional (about €2,290 in 2022) | Median first decision about 6 days (mostly desk decisions) | Best topical fit; high bar. Needs legal-domain depth and rigorous evaluation. Worth one try if section 5.3 goes well. |
| Journal of Information and Telecommunication (JIT) | Taylor & Francis (Ton Duc Thang University). Scopus Q1, CiteScore 6.7; IF 2.1 | TDTU says it covers the fee; DOAJ lists up to £925 (check) | First decision about 4 days; about 110 days after review; 5% acceptance | Strong and free, but very selective. A long shot. |
| TMLR (Transactions on Machine Learning Research) | JMLR family; reviewed openly on OpenReview | Free | Aims for a final decision in about 9 weeks | Accepts if “claims are supported by accurate and convincing evidence”. Fits only if we reframe around the evaluation findings (LLM judge, planner calibration). Disclose LLM use in a first-page footnote. |
| Journal of Computer Science and Cybernetics (VAST) | Vietnam Academy of Science and Technology; Scopus not confirmed (check) | Free | Review about 2 months | Solid national fallback; English only. |
| VNU Journal of Science: Computer Science and Communication Engineering | VNU Hanoi; indexing not confirmed (check) | Free | Not published | National fallback. |
| Language Resources and Evaluation | Springer. IF 1.8 | Free on the standard route | Median first decision 36 days | Only if we publish the human-labelled test set as a resource. |
| IEEE Access | IEEE. IF about 3.6 | $2,160 | First decision about 4–6 weeks | Fast and broad, but only if FPT pays the fee. |
| ACM TALLIP / ACM Digital Government (DGOV) | ACM | Open-access fee (ACM went fully open access); possible 50% discount for Vietnam (check) | Not found | Good topical fit (Asian languages; digital government). TALLIP rejects product descriptions without reproducibility. |

Green rows are the ones we recommend.

## 2.1 Suggested order

- Artificial Intelligence and Law, only if the human-labelled evaluation is strong. A desk rejection comes back in about a week.

- VJCS, the main target.

- Journal of Computer Science and Cybernetics or VNU JCSCE if VJCS rejects.

Alternative: if we decide the evaluation findings are more interesting than the system itself, write a focused paper for TMLR instead.

## 2.2 Avoiding predatory journals

“Pay a fee and get published” journals are common in our region, and a paper there can count against us. Red flags:

- Acceptance within days, with no real reviewer comments.

- Emailed invitations to submit.

- A fee that is the only real requirement.

- A name that copies a known journal.

Before submitting anywhere, confirm the journal on the Scopus Sources list, the Web of Science Master Journal List or DOAJ, not on the journal’s own website.

# 3. What each publisher says about AI

| Publisher (journals) | Rule | Where to disclose |
| --- | --- | --- |
| World Scientific (VJCS) | AI use allowed, including drafting, with mandatory human review. Say which tool and how it was used. Authors answer for originality and integrity. (Taken from a summary of the policy; check the original.) | Methods or similar section |
| Taylor & Francis (JIT) | Name the tool and version, how it was used and why. AI cannot be an author. | Methods; Acknowledgments if no Methods |
| Springer (AI & Law, LRE) | Document LLM use. Copy-editing of human-written text needs no declaration. No generative-AI images. | Methods section |
| TMLR | LLMs allowed; authors are responsible. Ideas, claims and results should be human-sourced. | Footnote on the first page |
| IEEE (IEEE Access) | Disclose AI-generated text, figures and code: which tool, which sections, how much. | Acknowledgments |
| ACM (TALLIP, DGOV) | Generative-AI content permitted but must be fully disclosed. | In the paper |

Draft disclosure we can adapt:

“The software described in this paper was developed with the help of an AI coding assistant (Claude Code, Anthropic). Parts of this manuscript were drafted with AI assistance; the authors reviewed, edited and verified all content and take full responsibility for it. Some test cases in the development and blind sets were written with LLM assistance (see Section X); the human-labelled evaluation set in Section Y was not.”

# 4. Where our paper stands

- Our strength: the system is real and honestly measured. We have blind test sets, confidence intervals, negative results (the LLM planner did not help) and a measured failure of LLM-as-judge.

- The current draft (docs/research_paper.md) is not submittable. It describes components the code does not contain, quotes unverified numbers from other papers, and compares our scores with other papers’ scores on different datasets.

# 5. What to fix, most important first

## 5.1 Integrity problems in the current draft

Any one of these can get the paper rejected, or worse, published with false claims under our names.

- Components that do not exist. The architecture section claims GPTCache on Redis, RouteLLM, vLLM, MCP and Qwen-2.5-7B. None of these is in the code. The real stack is Ollama with qwen3:4b-instruct-2507.

- Unverified related-work numbers. Many look invented, and the two that can be checked from memory are wrong: vLLM was compared against Orca and FasterTransformer, not HuggingFace TGI, and RAGAS was not validated against “human legal judges”. Check every number against the PDFs in docs/research paper/ or delete it, and confirm every reference exists.

- Cross-dataset comparison (draft §4.1). The table ranks our 75% against other papers’ scores on completely different datasets. Reviewers reject this on sight. Compare only on the same test set.

- Outdated numbers. The draft uses the 1,350-procedure snapshot; the official data is now version 3 (1,517 procedures). Items P1–P7 in docs/SUA_SLIDE_VA_BAI_BAO.md list the corrections.

## 5.2 Tell one sharper story

The draft tries to cover System 3, System 4 and more. Cut it to the Strict engine for Vietnamese administrative procedures. These are our most interesting and defensible findings:

- A 4B LLM planner did not beat the rules. It reported 0.99 confidence on 65% of its answers, including the wrong ones.

- A 7B LLM judge (RAGAS-style) is not trustworthy here. It caught only 51% of fabrications we planted on purpose, with κ = 0.02 agreement.

- “Rules decide, the LLM only phrases, a verifier checks every claim” works. The verifier kept 100% of the correct numbers.

- Text-to-SQL over one flat table works for a 4B model: 93% on our dedicated test set, because the model never has to write a JOIN.

- The honest gap: 98% on the tuning set, about 72–78% top-1 on blind sets, and clarification questions are right only about half the time.

## 5.3 Evaluation: the biggest weakness in substance

- No human has labelled any answer, and every test set was written by our team or by an AI agent. Collect 150–300 real citizen questions (family members, a ward office, public Q&A forums), have two people label them independently, and report their agreement (Cohen’s κ).

- Add real baselines on the same test set: BM25 alone, a multilingual dense retriever, and plain RAG with the same Qwen3-4B. Our old V10.6 version does not count as a baseline.

- Report properly: 95% confidence intervals (we already compute them) and latency under load, not only for a single user.

- Reproducibility: release the code and the test set, and state the data source and its licence.

- Ethics: citizen privacy (what PII masking does and does not catch) and the risk of wrong legal advice.

## 5.4 Writing quality

The draft reads like unedited AI output: bold text everywhere, phrases like “enterprise-grade” and “zero-hallucination”, absolute claims like “eliminates” that we cannot prove, and an internal codename (“Sys_3_4”) in the title. Reviewers penalize this style because it signals that nobody checked the content. Write plainly, make claims no bigger than the measurements, and give limitations their own section. A journal paper also needs a fuller related-work section and a complete method description, since there is no talk to fill the gaps.

# 6. What every reviewer checks

| Question on the review form | Where we stand | Action |
| --- | --- | --- |
| Is the contribution clear and new? | Spread over two systems | One story (5.2) |
| Is the method sound? | Good engineering, honestly measured | Remove false claims (5.1) |
| Are the baselines fair? | Only our own old version | Add 3 baselines (5.3) |
| Is the test data independent of tuning? | Blind sets exist, but LLM-written | Real queries + 2 human labellers |
| Can someone reproduce it? | Code in repo, not public | Release code + test set |
| Are limitations stated honestly? | Yes, our strength | Keep, as its own section |
| Are ethics covered? | Partly (PII masking measured) | Add privacy + wrong-advice risk |
| Is it clearly written? | Reads as AI-generated | Rewrite plainly (5.4) |

# 7. Eight-week timeline

| Week | Dates | Work |
| --- | --- | --- |
| 1 | 19–25 Oct | Remove false claims. Check every reference and number against the PDFs. Email VJCS (and JIT, about its fee) to ask current review times. |
| 2–3 | 26 Oct – 8 Nov | Collect 150–300 real citizen questions. Write a one-page labelling guide. |
| 3–4 | 2–15 Nov | Two people label independently; compute κ and resolve disagreements. |
| 5–6 | 16–29 Nov | Run the system and the three baselines on the new set; compute intervals and latency under load. |
| 7 | 30 Nov – 6 Dec | Rewrite as a journal paper around the single story in 5.2. Decide: AI & Law first, or straight to VJCS. |
| 8 | 7–18 Dec | Internal review, mentor read, reference check, AI disclosure. Submit. |
| — | Dec – Apr | Wait for the decision (typically 1–4 months), then revise and reply to reviewers. |

# 8. Still to confirm

- VJCS current review time and World Scientific’s AI policy wording (from its own site).

- Whether JIT is really free for us: TDTU says it covers the fee, but DOAJ lists up to £925.

- Scopus status of the Journal of Computer Science and Cybernetics and VNU JCSCE.

- ACM’s open-access fee and discount for Vietnam, if we consider TALLIP or DGOV.

- Whether FPT University pays publication fees for students (matters only for IEEE Access or ACM).

# Sources

- VJCS on DOAJ (no fee, open access)

- VJCS Scopus CiteScore 2024 (NTTU announcement)

- VJCS special issue and NTTU publication options

- World Scientific AI guidelines (summary)

- Artificial Intelligence and Law (Springer)

- Artificial Intelligence and Law — OA model and fee (MPDL)

- JIT — instructions for authors

- JIT — journal information and metrics

- JIT — society information (TDTU covers APC)

- JIT on DOAJ

- TMLR acceptance criteria

- TMLR FAQ

- Journal of Computer Science and Cybernetics (VAST)

- VNU Journal of Science: CS and Communication Engineering

- Language Resources and Evaluation (Springer)

- IEEE article processing charges

- ACM APC waiver countries

- ICAIL 2027 call (why conferences are out: in-person rule)

- Springer Nature AI policy

- IEEE guidelines for AI-generated text